## Process
Event | Business Process | Likely Scenario | Likelihood | Consequence | Risk Score
1 | Lost or Stolen Gyro Equipment | While in transit to the wellsite essential gyro equipment is lost or stolen | Low | Catastrophic | 8
2 | Damage to Calibration Equipment | Calibration equipment damaged causing the inability to perform pre and post job calibration verification and major calibration | Low | Serious | 4
3 | Damaged Gyro Survey Tool | During calibration verification tool is found to be damaged | Medium | Major | 9
3 | Loss of Essential Personnel | Personnel resign from essential position inside the company | Low | Serious | 4
4 | Multiple Jobs Scheduled | Multiple jobs scheduled causing a potential personnel and equipment shortage | Low | Major | 6
5 | Lost or Stolen PC | Huracan PC with client data or essential Huracan information lost or stolen | Medium | Major | 9
6 | Insufficient Gauge Equipment to Complete Sheduled Work | Insufficient equipment to perform a permanent gauge installation job. | Medium | Catastrophic | 12
7 | Gauge Installation Equipment Not Functional | Gauge installation equipment becomes damaged in transit to location and is unable to be repaired prior to the job starting | Low | Major | 4
8 | Potential Loss of Business Premises | Potential Loss of business premises due to catastophic event | Low | Catastrophic | 8
9 | Loss of Business Premises | Loss of business premises due to catastophic event | Low | Catastrophic | 8

## Lost Gyro
Lost or Stolen Gyro Equipment
Risk | Maximum Allowable Time: | Location | Category:
Minimal exposure in and around Roma. Maximum exposure while travelling long distances to jobs through populated areas. | Next revenue job requiring multiple gyro assets. Time to be assessed at the time of incident. | FBFV | SQ-Catastrophic
Risk Assessment
Likelihood | Consequence | Risk Rating
Low | Catastrophic | Medium
Immediate Response / Strategy
Response / Strategy
Back-up tools required. Secure storage facility of redundant tool sets. Transport facilities available to hotshot backup tools and equipment in the event of a loss of equipment.
Long Term Recovery Strategy
Response / Strategy
Investigate loss or theft. Rental of temporary replacement equipment. Purchase replacement equipment.

## Damaged Calibration Eq
Damaged Gyro Calibration Equipment
Risk | Maximum Allowable Time: | Location | Category:
Minimal exposure to risk as equipment is located in the workshop and locked after hours. | Next calibration cycle | FBFV | SQ-Serious
Risk Assessment
Likelihood | Consequence | Risk Rating
Low | Serious | Low
Immediate Response / Strategy
Response / Strategy
Use only tools within calibration period. Source second local calibration facility.
Long Term Recovery Strategy
Response / Strategy
Use only tools within calibration period. Seek exemption to use tools out of calibration period. Source second local calibration facility from Schlumberger or Weatherford. Purchase replacement calibration stand.

## Damaged Gyro
Damaged Gyro Survey Tool
Risk | Maximum Allowable Time: | Location | Category:
High likelihood of damaged equipment if personnel inadequately trained and equipment miss treated. | One Month | FBFV | SQ-Major
Risk Assessment
Likelihood | Consequence | Risk Rating
Medium | Major | Medium
Immediate Response / Strategy
Response / Strategy
Use only correct boxes and equipment to transport gyro equipment. Personnel must be trained on proper handling and storage of gyro equipment. Back-up tools required. Secure storage facility of redundant tool sets. Transport facilities available to hotshot backup tools and equipment in the event of a loss of equipment.
Long Term Recovery Strategy
Response / Strategy
Rental of temporary replacement equipment from Surewell, contact James Hunter and Shane Munyard. Purchase replacement equipment.

## Loss of Essential Personnel
Loss of Essential Personnel
Risk | Maximum Allowable Time: | Location | Category:
Potential Loss of personnel due to high employment rate within industry. | Prior to next service call-up. | FBFV | SQ-Serious
Risk Assessment
Likelihood | Consequence | Risk Rating
Low | Serious | Low
Immediate Response / Strategy
Response / Strategy
Utilise Vause personnel through cross training. Manager to be trained to perform service.
Long Term Recovery Strategy
Response / Strategy
Train personnel from EarthReach as call out contractors. Hire new gyro technician.

## Multiple Jobs Scheduled
Multiple Jobs Scheduled
Risk | Maximum Allowable Time: | Location | Category:
Low exposire due to cross training and personnel trained within Vause. | 4 months | FBFV | SQ-Major
Risk Assessment
Likelihood | Consequence | Risk Rating
Low | Major | Medium
Immediate Response / Strategy
Response / Strategy
Cross training of personnel within Huracan. Adequate tools available to perform multiple jobs.

## Lost Computer
Lost or Stolen Computer with Proprietary or Client Information
Risk | Maximum Allowable Time: | Location | Category:
Medium exposure due to laptops being portable. | Immediate. | FBFV | SQ-Major
Risk Assessment
Likelihood | Consequence | Risk Rating
Medium | Major | Medium
Immediate Response / Strategy
Response / Strategy
Personnel training on IT security. Computers to be locked when unattended. Back-up laptop and client data. Encryption on client and proprietary data.
Long Term Recovery Strategy
Response / Strategy
Investigate loss of laptop. Purchase replacement.

## Gauge Equipment
Insufficient Gauge Equipment to Complete Scheduled Work
Risk | Maximum Allowable Time: | Location | Category:
Medium potential due to high lead times on some items. | Prior to service. | FBFV | Catastrophic
Risk Assessment
Likelihood | Consequence | Risk Rating
Medium | Catastrophic | High
Immediate Response / Strategy
Response / Strategy
Source substitute gauges locally. Good planning and constant follow up with client. Hotshot equipment from manufacturer.
Long Term Recovery Strategy
Response / Strategy
Order equipment from manufacturer. Hold sufficient stock.

## Gauge Equipment (2)
Gauge Equipment Not Functioning
Risk | Maximum Allowable Time: | Location | Category:
Low exposure due to operation check prior to departure from workshop. | Immediate. | FBFV | SQ-Major
Risk Assessment
Likelihood | Consequence | Risk Rating
Low | Major | Medium
Immediate Response / Strategy
Response / Strategy
Equipment checked priot to departure from location. Back-up equipment taken to location. Have back-up TEC cable available in the unlikely event of TEC cable failure prior to installation.

## Potential Loss Premises
Potential Loss of Business Premises
Risk | Maximum Allowable Time: | Location | Category:
Potentially the largest risk to the company is the loss of the workshop and equipment stored within. | One Week | FBFV | SQ-Catastrophic
Risk Assessment
Likelihood | Consequence | Risk Rating
Low | Catastrophic | Medium
Immediate Response / Strategy
Response / Strategy
Remove all critical equipment to a safe location. Loan/Rent equipment required to load and remove critical equipment from premises to temporary laydown yard. Temporary laydown yard agreement with Vause

## Loss Premises
Loss of Business Premises
Risk | Maximum Allowable Time: | Location | Category:
Loss of and equipment stored within. | One Week | FBFV | SQ-Catastrophic
Risk Assessment
Likelihood | Consequence | Risk Rating
Low | Catastrophic | Medium
Immediate Response / Strategy
Response / Strategy
Remove all critical equipment to a safe location. Loan/Rent equipment required to load and remove critical equipment from premises to temporary laydown yard. Temporary laydown yard agreement with Vause
Long Term Recovery Strategy
Response / Strategy
Remove all critical equipment to a safe location. Loan/Rent equipment required to load and remove critical equipment from premises to temporary laydown yard. Temporary laydown yard agreement with Vause