## Table of Contents
Hazard Risk Register - Roma
Version | Author | Date | Revision Comments | Reviewers
1.0 | J. Hollingworth | 2013-09-26 | First Edition Hazard Risk Register | J. Hollingworth
1.1 | J. Hollingworth | 2015-09-29 | Review and update document | J. Hollingworth, D. Slater
1.2 | J. Hollingworth | 2017-05-05 | Additional risks and document update | J. Hollingworth
1.3 | J. Hollingworth | 2018-05-25 | Document review and update | J. Hollingworth, G. Humphreys, K. Rowbotham, J. Hetherington
1.4 | J. Hollingworth | 2018-06-06 | Document review and update with Responsible Parties and Measurement of Control | J. Hollingworth.
1.5 | J. Hollingworth | 2019-10-30 | Document review and Radiation Safety and Protection Plan added | J. Hollingworth.
1.6 | J. Hollingworth | 2023-01-18 | Addition of Explosive Operations | J. Hollingworth.
1.7 | J. Hollingworth | 2023-08-24 | Review document | J. Hollingworth.
1.8 | J. Hollingworth | 2025-01-13 | Review document - Noise | J. Hollingworth.
Table of Contents
Driving
Wellsite Operations
Emergency Response
Customer Data
Environment
Personnel & Training
Plant & Equipment
Lifting Operations
Working Conditions
Shop Operations
Radiation Operations
Explosive Operations
Noise

## Driving
Hazard Risk Register - Driving
Work Activity | Unwanted Event | Initial Risk | Prevention and Mitigation Controls | Residual Risk | Reference Documentation | Responsible Party | Measurement of Control (Validation and Frequency)
Driving | • Significant Injury or Fatality to Personnel • Asset Damage and Financial Loss • Client Impact | High (C5) | • Regular vehicle servicing and maintenance • Regular vehicle checks • Use alternative public transport where practical • Driver 4WD training • Company provided information on local traffic conditions / hazards, road works, etc. • Personal risk assessment of route prior to departure • Follow local Journey Management Plan • Follow Huracan Drug and Alcohol Policy • Use seat belt • Airbag and safety features • Driving Laws and national speed limits adhered to. • Local emergency services • Roma - Emergency Response Plan • Ensure adequate rest prior to departure • Ensure to update JM every two hours and or if conditions change • Engage 4WD off-road • If dust is encountered ensure to keep a safe distance behind dust cloud, never drive through a dust cloud • Drive to conditions | Low (E4) | • Land Transport Management Standard • Local Journey Management Plan • Emergency Management Plan | • Operations Manager • Drivers | • Journey Management in HIRD • Monthly KPI drivers performance • Emergency Management Plan

## Wellsite Operations
Hazard Risk Register - Wellsite Operations
Work Activity | Unwanted Event | Initial Risk | Prevention and Mitigation Controls | Residual Risk | Reference Documentation | Responsible Party | Measurement of Control (Validation and Frequency)
Wellsite Operations | • Significant Injury or Fatality to Personnel • Asset Damage and Financial Loss • Client Impact | High (C5) | • Ensure vehicle speed is below 10 km/hr • On arrival park vehicle in specific wellsite parking area • Update JM on arrival • Ensure that ER board is updated with individuals name tag or contractor tag • Consult with company man and discuss wellsite specific hazards such as high noise areas, automated rig equipment areas • Consult with rig HSE rep and perform wellsite / rig induction and identify ERP and rig specific ERP signals • Locate of ESD / Defibrillator • Ensure minimum PPE is worn at all time including but not limited to Hardhat / Safety Boots / Long sleeve shirts and pants / Gloves / Safety glasses • Origin - Remove watch and jewellery, hearing protection required • Wear hearing protection in high noise areas • Equipment to be checked in a secure area away from main rig activity • Connect and secure tools to ensure that tools do not fall during operational check • Follow SOP for operational check • Pre job safety meeting to ensure personnel understand task and risk associated with task • Permit to work to be completed as necessary • Conduct site assessment and step back 5 x 5 prior to rigging up equipment • Follow conveyance company specific procedures • Ensure lifting equipment is certified and fit for use • Ensure correct pressure equipment is used and in certification • Ensure pressure equipment is suitable for potential wellhead pressure • Exclusion areas around unit and authorised personnel only | Low (C2) | • Health and Safety Management Plan • Emergency Management Plan • Job specific SOP & JSA • Pre-departure Checklist • QA&QC Checklist | • Wellsite Personnel | • Client specific inductions in date • On the job training • SOP and JSA sign off sheet

## Emergency Response
Hazard Risk Register - Emergency Response
Work Activity | Unwanted Event | Initial Risk | Prevention and Mitigation Controls | Residual Risk | Reference Documentation | Responsible Party | Measurement of Control (Validation and Frequency)
Emergency Response | • Significant Injury or Fatality to Personnel • Environmental Damage • Financial Loss • Regulatory Compliance | Med (C4) | • Emergency Management Plan • Job specific SOP & JSA's • Journey Management and Land Transport Standard • Pre-job planning meeting & HSE document review- JSA, SOP, Checklists • Client specific safety training and Emergency Management | Low (E4) | • Health and Safety Management Plan • Emergency Management Plan • Job specific SOP & JSA | • Operations Manager • Emergency response team | • EMP annual drill, audit and response

## Customer Data
Hazard Risk Register - Customer Data
Work Activity | Unwanted Event | Initial Risk | Prevention and Mitigation Controls | Residual Risk | Reference Documentation | Responsible Party | Measurement of Control (Validation and Frequency)
Customer Data | • Client Impact • Loss of Reputation | Med (B2) | • Password protection PC and Acquisition systems • Regular security updates • Data encryption • No client data on public domain • Use document classification • Clear traceability on customer labelling | Low (D2) | • Health and Safety Management Plan | • Operations Manager • Technicians | • EMP annual drill, audit and response

## Environment
Hazard Risk Register - Environment
Work Activity | Unwanted Event | Initial Risk | Prevention and Mitigation Controls | Residual Risk | Reference Documentation | Responsible Party | Measurement of Control (Validation and Frequency)
Environment | • Environmental Damage • Financial Loss • Regulatory Compliance | Med (C4) | • Emergency Management Plan • Chemical storage as per Spill Control and prevention document • Training and competency assesments • Spill control drill and training • Substition for hazardeous checmicals • Clearr labells on chemicals • MSDS updated and used • Recycle and re-use where possible • Disposal of checmicals at approved locations | Low (E4) | • Huracan Environmental Management Plan • Huracan Environmental Training Requirements • Huracan Spill Prevention and Control Plan • Emergency Management Plan • MSDS | • Operations Manager • All personnel • Emergency Response Team | • EMP annual drill, audit and response

## Personnel & Traning
Hazard Risk Register - Personnel & Training
Work Activity | Unwanted Event | Initial Risk | Prevention and Mitigation Controls | Residual Risk | Reference Documentation | Responsible Party | Measurement of Control (Validation and Frequency)
Personnel & Training | • Financial Loss • Personal Injury • Asset Damage • Regulatory Compliance | Low (C2) | • Internal training and mentoring of personnel • Client specific training modules • Industry safety training • Competency assessment and testing • Job description and employment letters • Annual personnel review and assessment | Low (E2) |  | • Operations Manager • All personnel | • Training Matrix

## Plant & Equipment
Hazard Risk Register - Operating Plant & Equipment
Work Activity | Unwanted Event | Initial Risk | Prevention and Mitigation Controls | Residual Risk | Reference Documentation | Responsible Party | Measurement of Control (Validation and Frequency)
Operating Plant & Equipment | • Significant Injury or Fatality to Personnel • Asset Damage and Financial Loss • Client Impact | Med (C4) | • Exclusion zone set for operating plant with authorised personnel only • Equipment guards in-place and adequate • Pre-job planning meeting & HSE document review- JSA, SOP, Checklists • Competent equipment operator • Control panel adequately labelled • Rated & Verified lifting equipment in test • Equipment positioning on level ground • Licence review if required • Site Safety Manger appointed as required • WPTW Lifting Permit • Maintenance personnel adequately trained to perform maintenance • Power system isolated prior to maintenance | Low (E4) | • Health and Safety Management Plan • Emergency Management Plan | • Operations Manager • All personnel | • Annual First Aid training • SOP&JAS sign off sheet • Site Safety Manager • Permit to Work

## Lifting Operations
Hazard Risk Register - Lifting Operations
Work Activity | Unwanted Event | Initial Risk | Prevention and Mitigation Controls | Residual Risk | Reference Documentation | Responsible Party | Measurement of Control (Validation and Frequency)
Lifting Operations | • Significant Injury or Fatality to Personnel • Asset Damage and Financial Loss • Client Impact | Med (C4) | • Exclusion zone set for lifting operations • Pre-job planning meeting • Competent operator / dogger • Rated & Verified lifting equipment in test • Lift plan (as required) • QHSE Resource (Supporting) Documentation - JSA, SOP, Checklists • Lifesaving Rule - NEVER work / walk under suspended load, always have a way out • Tag lines / hands off equipment to remove personnel from line of fire & eliminate risk of pinch points / injuries to hands or personnel • WPTW Lifting Permit • DROPs Inspections | Med (D4) | • Health and Safety Management Plan • Emergency Management Plan • Job specific SOP & JSA | • Operations Manager • All personnel | • Annual lifting equipment audit performed by third party • Pre-job inspection

## Working Conditions
Hazard Risk Register - Working Conditions
Work Activity | Unwanted Event | Initial Risk | Prevention and Mitigation Controls | Residual Risk | Reference Documentation | Responsible Party | Measurement of Control (Validation and Frequency)
Working Conditions | • Personal Injury • Regulatory Compliance | Med (B4) | • Huracan Drug and Alcohol Policy • Drug and Alcohol testing • For cause investigation and testing • Huracan Disciplinary Matrix • Roster and Fatigue Management • Shared duties • Heat Stress awareness management • Minimise work time on 'Red Alert' days • Adequate fluid available and monitor intake | Low (D4) | • Health and Safety Management Plan • Emergency Management Plan | • Operations Manager • All personnel | • Heat stress annual training • Fatigue management • Roster staff plan • For cause drug and alcohol testing

## Shop Operations
Hazard Risk Register - Shop Operations
Work Activity | Unwanted Event | Initial Risk | Prevention and Mitigation Controls | Residual Risk | Reference Documentation | Responsible Party | Measurement of Control (Validation and Frequency)
Shop Operations | • Environmental Damage • Financial Loss • Regulatory Compliance | Med (C4) | • Workshop Induction • Visitor sign on and inductions • Speed limit for foot and vehicle areas • Loading / Unloading area • Housekeeping • Hazardous chemical storage • Spill control and prevention training • Waste management and recycling • Pre-job planning and hazard identification | Low (E4) | • Health and Safety Management Plan • Emergency Management Plan • Huracan Environmental Management Plan • Huracan Environmental Training Requirements • Huracan Spill Prevention and Control Plan • Emergency Management Plan • MSDS | • Operations Manager • All personnel | • Heat stress annual training • Annual KPI's • Emergency management plan drill and audit reposnse

## Radiation Operations
Hazard Risk Register - Radiation Operations
Work Activity | Unwanted Event | Initial Risk | Prevention and Mitigation Controls | Residual Risk | Reference Documentation | Responsible Party | Measurement of Control (Validation and Frequency)
Radiation operations | • Environmental Damage • Financial Loss • Regulatory Compliance | Med (C4) | • Workshop Induction • Visitor inductions • Loading / Unloading area • Radiation User Licensing • Training • Radiation Storage Area • Pre-job planning and hazard identification | Low (E4) | • Health and Safety Management Plan • Radiation Safety and Protection Plan • Huracan Radiation Training Requirements • Queensland NM009 user licence • Site Radiation Survey | • Operations Manager • All personnel | • Emergency management plan drill and audit reposnse

## Explosive Operations
Hazard Risk Register - Explosive Operations
Work Activity | Unwanted Event | Initial Risk | Prevention and Mitigation Controls | Residual Risk | Reference Documentation | Responsible Party | Measurement of Control (Validation and Frequency)
Explosive Wireline Operations | Unplanned explosion event on surface causing; • Significant Injury • Fatality • Equipment / Property Damage • Financial Loss • Regulatory Impact | High (C5) | • Training to ensure competency in explosives handling including transport; • Resource Documentation - JSA's, SOP's, Checklists, Explosives Safety & Security Plan; • Comply to HAZNO & API RP 67; • Pre Start Safety Meeting to discuss & agree on operations & confirm communications with all involved parties (Rig Crew, OCR) including parties involvement during troubleshooting operations (i.e. advise rig crew of failure & bring to surface as quickly as possible); • WPTW Rev 3 (additional resource control); • Check weather conditions / forecast - DO NOT operate explosives within 30min of known storm (electrical, dust etc); • Exclusion zone established & communicated to all on-site parties; • RF Safe System; | Med (D4) | • Explosive Safety and Security Plan • Personnel Training and Competency Requirement • Health and Safety Management Plan • Emergency Management Plan • Job specific SOP & JSA • Pre-Job Safety Meetings • Explosive Checklist • Explosive Safety Key • Wellsite Permit To Work (WPTW) | • Operations Manager and responsible for ensuring personnel are competent & necessary resources are available, • Personnel involved in the transport and use of explosives. | • All required personnel to hold relevant (State dependant) current Explosives license for use (renewed 3-5 years as per State regulation), • On-the-job training in Huracan procedures conducted by Competent person. • KPI's - annual; • Permit review during audit (quarterly) • Emergency Management exercise drills as per Audit & Inspection schedule
Wireline Perforating | Unplanned Explosive Initiation Downhole causing; • Financial loss • Quality non-conformance • Equipment damage • Regulatory Impact | Med (B3) | • Training to ensure competency in explosives handling including transport through licencing and mentoring; • Resource Documentation - JSA's, SOP's, Checklists, Explosives Safety & Security Plan; • Comply to HAZNO & API RP 67; • Pre Start Safety Meeting to discuss & agree on operations & confirm communications with all involved parties (Rig Crew, OCR) including parties involvement during troubleshooting operations (i.e. advise rig crew of failure & bring to surface as quickly as possible); • Current revision of the WPTW system (additional resource control); • Check weather conditions / forecast - DO NOT operate explosives within 30min of known storm (electrical, dust etc); • Exclusion zone established & communicated to all on-site parties; • RF Safe System; • Good primary and secondary depth control; | Low (D3) | • Explosive Safety and Security Plan • Health and Safety Management Plan • Personnel Training and Competency Requirement • Emergency Management Plan • Job specific SOP & JSA • Pre-Job Safety Meetings • Explosive Checklist • Explosive Safety Key • Wellsite Permit To Work (WPTW) | • Operations Manager and responsible for ensuring personnel are competent & necessary resources are available, • Personnel involved in the transport and use of explosives. | • All required personnel to hold relevant (State dependant) current Explosives license for use (renewed 3-5 years as per State regulation), • On-the-job training in Huracan procedures conducted by Competent person. • KPI's - annual; • Permit review during audit (quarterly) • ERP exercise drills as per Audit & Inspection schedule
Wireline Perforating | Failure of Explosives to detonate when initiated; • Financial loss to operating company and Huracan • Quality non-conformance • Equipment damage • Regulatory Impact | Med (C4) | • Explosives Stock Management (rotate stock to use oldest first ensuring all stock within allowed best before date) • Training to ensure competency in explosives handling including transport; • Resource Documentation - JSA's, SOP's, Checklists, Explosives Safety & Security Plan; • Comply to HAZNO & API RP 67; • Pre Start Safety Meeting to discuss & agree on operations & confirm communications with all involved parties (Rig Crew, OCR) including parties involvement during troubleshooting operations (i.e. advise rig crew of failure & bring to surface as quickly as possible); | Med (D4) | • Explosive Safety and Security Plan • Health and Safety Management Plan • Personnel Training and Competency Requirement • Emergency Management Plan • Job specific SOP & JSA • Pre-Job Safety Meetings | • Operations Manager and responsible for ensuring personnel are competent & necessary resources are available, • Personnel involved in the transport and use of explosives. | • All required personnel to hold relevant (State dependant) current Explosives license for use (renewed 3-5 years as per State regulation), • On-the-job training in Huracan procedures conducted by Competent person.; • KPI's - annual;
Explosive Storage | Inappropriate handling and storage • Uncontrolled release of explosives • Significant Injury • Fatality • Equipment damage • Environmental damage • Regulatory Impact | Med (C4) | • Removal of all ignition sources within loading area • Secure bunker for storage meeting the Qld Explosives Regulations standards. • Key to bunker / magazine holder is held by Operations Manager in a secured place. • Dedicated safe arming area • Effective communication with all affected parties to ensure understanding of risk / operation & subsequent controls in place to manage the risk i.e. exclusion zone, radios off etc. • Excellent housekeeping • Trained & competent workers • QHSE Resource (Supporting) documentation i.e. JSA's & SOP's, Checklists • Signage (exclusion zone) • WPTW Rev 3 | Low (E4) | • Explosive Safety and Security Plan • Health and Safety Management Plan • Personnel Training and Competency Requirement • Emergency Management Plan • Job specific SOP & JSA • Pre-Job Safety Meetings • Explosive Checklist • Explosive Key Security • Audit of record keeping. • Wellsite Permit To Work (WPTW) | • Operations Manager and responsible for ensuring personnel are competent & necessary resources are available, • Personnel involved in inventory management. | • All required personnel to hold relevant (State dependant) current Explosives license for use (renewed 3-5 years as per State regulation), • On-the-job training in Huracan procedures conducted by Competent person. • KPI's - annual; • Bunker Physical count and reconciliation monthly.
Explosives Transport | Transport of explosives • Equipment damage; • Regulatory Impact | Med (D4) | • Explosives Handling License (use, storage & transport); • Competent Wireline person to load guns (as required) safely; • Suitable vehicle (registered to carry explosives) with adequate storage compartment (locked) for detonators; • Armed guns secured to vehicle & locked; • Trained & Competent personnel; • QHSE Resource (Supporting) Documentation JSA's, SOP's, Checklists; • Appropriate Load restraints (all explosives components must be secured & / or supervised at all times; • Explosives Risk Categories for Explosives stored / transported & used are Category 1 (Low Risk) "All other Division 1.1" of ≤ 5kg allowing transportation of armed guns without the additional requirements as outlined within the legislation (See Appendix G of ESSP). • Compliance with ADG Code & Legislation | Low (E4) | • Explosive Safety and Security Plan • Health and Safety Management Plan • Personnel Training and Competency Requirement • Emergency Management Plan • Job specific SOP & JSA | • Operations Manager and responsible for ensuring personnel are competent & necessary resources are available, • Personnel involved in the transport of explosives. | • All required personnel to hold relevant (State dependant) current Explosives license for use (renewed 3-5 years as per State regulation), • On-the-job training in Huracan procedures conducted by Competent person. • KPI's - annual; • ERP exercise drills as per Audit & Inspection schedule
Explosive Security | Loss of Explosives Due to Poor Security • Regulatory Impact | Med (C4) | • Secure bunker for storage meeting the Qld Explosives Regulations standards. • Key to bunker / magazine holder is held by Operations Manager in a secured place. • Effective communication with all affected parties to ensure understanding of risk / operation & subsequent controls in place to manage the risk during storage, loading and transport of explosives. • Excellent housekeeping and record keeping. • Trained & competent workers • QHSE Resource (Supporting) documentation i.e. JSA's & SOP's, Checklists • Review to be undertaken in the event of significant security event and appropriate steps taken to review and mitigate risk. | Low (E4) | • Explosive Safety and Security Plan • Personnel Training and Competency Requirement • Emergency Management Plan • Job specific SOP & JSA • Pre-Job Safety Meetings • Explosive Checklist | • Operations Manager and responsible for ensuring personnel are competent & necessary resources are available, • Personnel involved in inventory management. | • All required personnel to hold relevant (State dependant) current Explosives license for use (renewed 3-5 years as per State regulation), • On-the-job training in Huracan procedures conducted by Competent person. • KPI's - annual; • Permit review during audit (quarterly)

## Noise
Hazard Risk Register - Explosive Operations
Work Activity | Unwanted Event | Initial Risk | Prevention and Mitigation Controls | Residual Risk | Reference Documentation | Responsible Party | Measurement of Control (Validation and Frequency)
Noise - To be assessed. | High Plant Equipment Noise Level leads to Personnel loss of hearing. | Med (A2) | Plant and Equipment Noise Assessment to be performed on following relevant Huracan Plant Equipment. - Cable Spooling Unit - Wireline Unit - Pressure Test Equipment Equipment with >85dB of noise musy have mitigation measures implemented. Refer to HSMP and Managing Noise and Preventing Hearing Loss at Work - Code of Practice. | Low (D2) | Huracan Halth and Safety Management Plan Managing Noise and Preventing Hearing Loss at Work - Code of Practice. | Location Manager | Emplyment and 2 yearly Personnel Audiometric Testing.